## Home
Bank of Abyssinia Production Test
| Testing Start Date / Time: | **/**/****
| Testing End Date: | **/**/****
| Service type | *815# USSD
| Name of Tester/s: | BOA team
Date: **/**/****
# | UAT Cases | # of Functionalities | Pass | Fail | Not checked
1 | Login | 2 | 2
2 | Account | 3 | 3
3 | Transfer | 33 | 22 |  | 11
6 | Airtime topup | 7 | 4 |  | 3 | Date 10/02/2025 USSD UAT
7 | Utility | 22 | 9 |  | 13 | Total Functionality | 70
8 | SETTING | 3 | 3 |  |  | Not checked (Third party unavailability) | 27
Total | [5 empty] | Failed | -
Total tested functionalities | [5 empty] | Pass | 43
Percentage | [5 empty] | Percentage | 100%
Date 30/08/2024 USSD UAT
[6 empty] | Total Functionality | 30
[6 empty] | Not checked (Test data) | 6
[6 empty] | Failed | 13
[6 empty] | Pass | 12
[6 empty] | Percentage | 46
Date 16/09/2024 USSD UAT
[6 empty] | Total Functionality | 30
[6 empty] | Not checked (Test data&env't) | 8
[6 empty] | Failed | 1
[6 empty] | Pass | 21
[6 empty] | Percentage | 95

## login
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
L001 | Open USSD | Dial *815# & select the "1" for login after the push notification is displayed | A push notification will be displayed requesting the customer to enter PIN to log in. | Pass |  | Pass
|  | Enter PIN | A push notification will be displayed along with the list of services provided
Negative test |  | First time sign in should force for pin update |  | Pass
L002 | Sign out | Dial *815# & select the "1" for login after the push notification is displayed | A push notification will be displayed requesting the customer to enter PIN to log in. | Pass
|  | Enter PIN | A push notification will be displayed along with the list of services provided
|  | Select on the Exit option | A succsesful logout notification will be displayed
Date | Functionalities | # of Functionalities | Pass | Failed | Not Executed
| Login | 2 | 2
| Negative test | 1 | 1

## Accounts
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
A001 | Go to the accounts menu | Choose the accounts section from the homepage menu of the app. | list of accounts associated with the customer ID will be displayed. | Pass
A002 | View transactions | Choose the accounts section from the homepage menu of the app. | list of accounts associated with the customer ID will be displayed. | Pass
|  | Choose a specific account | The list of recent transactions will be displayed
A003 | View transaction details | Choose the accounts section from the homepage menu of the app. | list of accounts associated with the customer ID will be displayed. | Pass
|  | Choose a specific account | The list of recent transactions will be displayed
|  | Choose a specific transaction | Details about the transaction will be displayed
Date | Functionalities | # of Functionalities | Pass | Fail | Not Executed
| Accounts | 3 | 3

## Transfer
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
T001 | Transfer menu | Choose the transfer option in the home page | List of transfer options will be displayed | Pass
T002 | Transfer within BoA | Choose the Transfer option from the list of transfer options displayed | A space will be provided to input the destination account along with the send & cancel option | Pass
|  | Choose from account from the list of accounts | A space will be provided to input amount to be sent along with the send & cancel option
|  | Enter amount & click proceed | A space will be provided to upload remark for the transaction
|  | Enter a remark for the transfer | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
|  | within Boa transfer aside from the cumulative limit should not allow the user to transfer more than500k |  | Pass
|  | Transfer to USD accounts shouldn't be alowed with USSD service platform |  | Pass
T003 | ATM withdrawal | Select the ATM withdrawal option from the list of transfer options displayed | List of account/s will be displayed along with inputting section,send & terminate session alternatives | Pass
|  | Select account | Amount setting screen will be displayed
|  | Set amount to be sent | A confirmation notification will be along with a confirmation & cancelation option
|  | Review details & confirm the withdrawal | A succses screen will be displayed along with the transaction details
Negative scenario |  | Attempt to transfer exceeding Maximum limit (>8000) should not be applicable and throw error |  | Pass
|  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
T004 | Transfer to telebirr | Select the Load to telebirr option from the list of transfer options displayed | List of account/s will be displayed along with inputting section,send & terminate session alternatives | Not Executed | Third party server unavailability to be tested on prod
|  | Select account | The screen with a section for setting amount will be shown
|  | Set amount | A confirmation screen will be displayed
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not Executed | Third party server unavailability to be tested on prod
|  | The entered telebirr user should be verified and if it's not the system should throw an error accordingly |  | Not Executed
|  | Attempt to transfer exceeding Maximum limit (>30,000) should not be applicable and throw error |  | Not Executed
T005 | Transfer to MPESA | Select the Transfer to MPESA option from the list of transfer options displayed | A Safaricom number inputting section will be displayed | Not Executed | Third party server unavailability to be tested on prod
|  | Enter a phone number with MPESA account | List of account/s will be displayed along with inputting section,send & terminate session alternatives
|  | Select account | The screen with a section for setting amount will be shown
|  | Enter amount & click proceed | A space will be provided to upload remark for the transaction
|  | Enter a remark for the transfer | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not Executed | Third party server unavailability to be tested on prod
|  | The entered M-PESA user should be verified and if it's not the system should throw an error accordingly |  | Not Executed
|  | Attempt to transfer exceeding Maximum limit (>30,000) should not be applicable and throw error |  | Not Executed
T006 | Local money transfer | Choose the Local money transfer option in the transfer section | List of account/s will be displayed
|  | Select debit account | A section will be provided to upload the first name of the beneficary
|  | Enter first name | A section will be provided to upload the Last name of the beneficary
|  | Enter last name | Assection will be displayed to upload the beneficary phone number
|  | Enter phone number | The screen with a section for setting amount will be shown
|  | Enter amount | A confirmation screen will be displayed
|  | Review details & confirm the transfer | Succes screen will be displayed along with details of the transaction
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit
T007 | Transfer to Awach | Choose the Awach option in the transfer section | A section will be provided to upload awach account number used by the customer | Not Executed | Third party server unavailability to be tested on prod
|  | Enter awach account | List of account/s will be displayed
|  | Select debit account | The screen with a section for setting amount will be shown
|  | Enter amount | A confirmation screen will be displayed
|  | Review details & confirm the transfer | Succes screen will be displayed along with details of the transaction
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not Executed | Third party server unavailability to be tested on prod
|  | Account of the user to be transffered to should be validated from the third party server |  | Not Executed
T008 | Transfer to other bank menu | Choose the transfer to other bank option in the home page | List of transfer options will be displayed | Pass
T009 | Instant transfer to other bank | Choose the Instant transfer option from the list of transfer to other bank options displayed | List of banks will be displayed | Pass
|  | Select bank | A space will be provided to input the destination bank account along with the send & cancel option
|  | Enter account number | List of debit account/s will be displayed along with inputting section,send & terminate session alternatives
|  | Select account number | The screen with a section for setting amount will be shown
|  | Set amount | A confirmation screen will be displayed
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenarios |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass | Third party server unavailability to be tested on prod
|  | Instant transfer to other banks aside from the cumulative limt should not allow user to transfer more than 25K for one time transfer |  | Pass
|  | Instant transfer to other banks aside from the cumulative limit should not allow the user to transfer more than 50k within a day |  | Pass
|  | Transfer TO USD accounts shouldn't be alowed with USSD service platform |  | Pass
T010 | Non-Instant transfer to other bank | Choose the Non Instant transfer option from the list of transfer to other bank options displayed | List of debit account/s will be displayed along with inputting section,send & terminate session alternatives | Pass
|  | Select account number | Recipent name inputting section will be dispalyed
|  | Enter recipent name | List of banks will be displayed
|  | Select bank | The screen with a section for setting amount will be shown
|  | Set amount | A confirmation screen will be displayed
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenarios |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
|  | Instant transfer to other banks aside from the cumulative limt should not allow user to transfer more than 50K for one time transfer |  | Pass
|  | Instant transfer to other banks aside from the cumulative limit should not allow the user to transfer more than 200k within a day |  | Pass
|  | Transfer TO USD accounts shouldn't be alowed with USSD service platform |  | Pass
T011 | Transfer to own account | Choose the transfer own account option in the home page | List of account/s will be displayed | Pass
|  | Select account to be debited | List of account/s will be displayed
|  | Select account to be credited | Transaction amount setting screen will be displayed
|  | Enter amount & click proceed | A space will be provided to upload remark for the transaction
|  | Enter a remark for the transfer | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the transfer | A succses screen will be displayed along with the transaction details
Negative scenario |  | Even if the commulative is reached own account transfer should work with any amount |  | Pass
|  | If the account is inactive the process should throw an error and abort |  | Pass
Date | Functionalities | # of Functionalities | Pass | Failed | Not Excuted
| Transfer | 10 | 7 |  | 3
| Negative tests | 23 | 15 |  | 8

## Airtime topup
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
AT001 | Airtime-topup menu | Choose the Airtime topup option in the home page | Ethiotelecom & safaricom airtome topup options will be displayed | Pass
AT002 | Ethiotelecom airtime topup | Choose the Ethiotelecom airtime topup option in the Airtime topup page | List of accounts will be displayed | Pass
|  | Select account to be debited | Phone number inputing section will be displayed
|  | Enter phone number | The screen with a section for setting amount will be shown
|  | Enter amount | A confirmation screen will be displayed
|  | Review details & confirm the topup | Succes screen will be displayed along with details of the transaction
Negative scenario |  | Should not allow the user to top-up if daily commulative limit is reached |  | Pass
|  | Phone number should start as 09 if not the process should throw error message to the user |  | Pass
AT004 | Safaricom airtime topup | Choose the Safari airtime topup option in the Airtime topup page | List of accounts will be displayed | Not Executed | Third party server unavailability to be tested on prod
|  | Select account to be debited | Phone number inputing section will be displayed
|  | Enter phone number | The screen with a section for setting amount will be shown
|  | Enter amount | A confirmation screen will be displayed
|  | Review details & confirm the topup | Succes screen will be displayed along with details of the transaction
Negative scenario |  | Should not allow the user to top-up if daily commulative limit is reached |  | Not Executed
|  | Phone number should start as 07 if not the process should throw error message to the user |  | Not Executed
Date | Functionalities | # of Functionalities | Pass | Failed | Not excuted
| Airtime topup | 3 | 2 |  | 1
| Negative test | 4 | 2 |  | 2

## Utility
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
UTL001 | Utility menu | Choose the Airtime topup option in the home page | List of utility payments will be displayed | Pass
UTL002 | Ethiotelecom post payment | Choose the Ethiotelecom postpayment option in the utility section | Phone number or account number choosing section will be displayed | Pass | Third party server unavailability to be tested on prod
|  | Enter phone number or account key | List of account/s will be displayed
|  | Select debit account | Remark inputting section will be displayed
|  | Enter a remark for the payment | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Pass | Third party unavilability
|  | Account key/Phone number should be verified from third party side, if not it should throw an error |  | Pass | Third party unavilability
UTL003 | DSTV bill payment | Choose the DSTV option in the utility section | Smart card number inputting section will be displayed | Pass | Third party unavilability
|  | Input smart card number | List of packages & outstanding bills will be displayed
|  | Select package/bill payment option | The time scale for the payment will be displayed
|  | Select the time scale | List of account/s will be displayed
|  | Select debit account | Remark inputting section will be displayed
|  | Enter a remark for the payment | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Pass | Third party unavilability
|  | The smart card number entered should be verified from third party side, if not it should throw an error |  | Pass | Third party unavilability
UTL004 | Websprix bill payment | Choose the Websprix bill payment option in the utility section | Clinet ID or phone number selecting section will be displayed | Pass
|  | Enter phone number or clinet ID | List of account/s will be displayed
|  | Select debit account | Remark inputting section will be displayed
|  | Enter a remark for the payment | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Pass
|  | Client ID/Phone number should be verified from third party side, if not it should throw an error |  | Pass
UTL005 | Airlines payment | Choose theEthiopian airlines option in the utility section | Order ID inputting section will be displayed | Not Executed | Third party unavilability
|  | Enter Order ID | List of account/s will be displayed
|  | Select debit account | Remark inputting section will be displayed
|  | Enter a remark for the payment | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not Executed | Third party unavilability
|  | PNR entered should be verified from third-party side, if not it should throw an error |  | Pass
UTIL 006 | Water bill payment | Choose the water bill payment option in the utility section | List of cities will be displayed | Not Executed | Third-party unavailability New cities have been Added
|  | Select city | Bill number inputting section will be displayed
|  | Enter bill number | Remark inputting section will be displayed
|  | Enter remark | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not Executed | Third party unavilability
|  | City list updated with currentlyrequested cities (If any) |  | Pass
|  | Choosen City and entered bill number should be validated and if wrong the system should throw an error |  | Pass
UTIL 007 | Federal housing | Choose the federal housing option in the utility section | Bill number inputting section will be displayed | Not Executed | Third party unavilability
|  | Enter bill number | Remark inputting section will be displayed
|  | Enter remark | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not Executed | Third party unavilability
|  | Bill ID should be verified from third party side, if not it should throw an error |  | Pass
UTIL008 | Canal plus | Choose the canal plus option in the utility section | subscription number inputting section will be displayed | Not Executed | Third party unavilability
|  | Enter subscription number | List of packages will be displayed (Existing,desta, feshta)
|  | Select the prefered package | Amount displayed along with remark inputting section will be displayed
|  | Enter remark | A confirmation notification will be displayed along with a confirmation & cancelation option
|  | Review details & confirm the payment | A succses screen will be displayed along with the transaction details
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not Executed | Third party unavilability
|  | The smart card number entered should be verified from third party side, if not it should throw an error |  | Pass
Date | Functionalities | # of Functionalities | Pass | Fail | Not excuted
| Utilities | 8 | 2 |  | 6
| Negative test | 14 | 7 |  | 7

## CR doc
*815# USSD test(Aug 30's CR)
S/N | Module | Excuted Features | Expected Results | Status | Remark
1 | Login | Click on "Login" button | Field to fill with credential will be displayed | Pass
|  | Enter your pin | Click on continue button and the page will get displayed with managing menus
Negative test |  | First time sign in should force for pin update |  | Pass
2 | My Accounts | Enter the number entitled with "My accounts" and click "send" button | List of accounts associated with the user's customer ID will be displayed | Pass
|  | Select an account to check the transaction made within | Transaction of the given account will be displayed with date they were made
3 | Utilities | Enter the number entitled with "Utilities" and click "send" button | List of utility payment service menus will be displayed | pass
4 | Transfer | Enter the number entitled with "Transfer" and click "send" button | List of fund transfering options and money load wallets will be displayed | pass
5 | other bank Transfer | Enter the number entitled with "Transfer to other bank" and click "send" button | List of to other bank fund transfering options will be displayed | pass
6 | Airtime Topup | Enter the number entitled with "Airtime Topup" and click "send" button | List of Top up purchasing option service menus will be displayed | pass
7 | Exchange Rates | Enter the number entitled with "Exchange Rates" and click "send" button | List of exchange rate description will be displayed with next and previous option | pass
8 | My service | Enter the number entitled with "My service" and click "send" button | "Change Pin" and "De-subscribe" service will be displayed | pass
9 | Loan | Enter the number entitled with "Loan" and click "send" button | MESMER loan and an option to repay active loan "Repayment" will be displayed | pass
S/N | Service | Excuted Functionalities | Expected results | Status | Remark
1 | DERASH (Water Bill) | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Menu not found
|  | Enter the number entitled with "DERASH" and click "send" button | select city and enter client reference ID
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit
City list updated with currently requested cities (If any)
Choosen City and entered bill number should be validated and if wrong the system should throw an error
2 | Awach | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "AWACH" and click "send" button | Enter account number of the beneficiary and account holder name will be displayed
|  | confirm account holder name by sending "1" | Amount entering screen will be displayed
|  | enter amount and click on "send" button | Remark entering screen will be displayed
|  | enter remark and click on the "Send" button | success for the payment with TXN reference will be displayed
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not checked
|  | Account of the user to be transffered to should be validated from the third party server |  | Not checked
3 | Canal Plus | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Canal Plus" and click "send" button | Enter client reference ID
|  | Package reference list will be displayed | select package preference (Existing, Desta, Feshta)
|  | Detail of the ID and selected package purchase amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | The smart card number entered should be verified from third party side, if not it should throw an error |  | Pass
4 | Water | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Water" and click "send" button | select city and enter client reference ID
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked
|  | City list updated with currently requested cities (If any) |  | Pass
|  | Choosen City and entered bill number should be validated and if wrong the system should throw an error |  | Pass
5 | Airlines | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Airlines" and click "send" button | Enter client order ID
|  | Detail along with payment amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | enter remark and click on the "Send" button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | PNR entered should be verified from third-party side, if not it should throw an error |  | Pass
6 | DSTV | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile(to be tested on prod)
|  | Enter the number entitled with "DSTV" and click "send" button | Enter client Smart card number
|  | Package reference list will be displayed | select package preference (including an option for the Existing package)
|  | a list for subscription time interval (monthly, anually… etc) | select and confirm with "Send" button
|  | Detail of the ID and selected package purchase amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | The smart card number entered should be verified from third party side, if not it should throw an error |  | Pass
7 | Websprix | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Pass
|  | Enter the number entitled with "Websprix" and click "send" button | Enter client ID/Websprix phone number
|  | Field to enter bill number will be displayed | enter bill number and click "Send" button
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Pass
|  | Client ID/Phone number should be verified from third party side, if not it should throw an error |  | Pass
8 | Ethiotel bill | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Ethiotelecom bill" and click "send" button | Enter bill phone number/Account key
|  | Field to enter bill number will be displayed | enter bill number and click "Send" button
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | Account key/Phone number should be verified from third party side, if not it should throw an error |  | Pass
9 | FHC (Federal Housing) | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "FHC" and click "send" button | Enter BILL reference
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
Negative scenario |  | The comulative limit should not allow user to pay more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | Bill ID should be verified from third party side, if not it should throw an error |  | Pass
10 | Transfer to other BOA acc | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Pass
|  | Enter the number entitled with "Transfer to other BOA acc" and click "send" button | Enter beneficiary account and verrify
|  | select from account to debit TXN | Enter amount to be transferred and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
|  | within Boa transfer aside from the cumulative limit should not allow the user to transfer more than500k |  | Pass
|  | Transfer to USD accounts shouldn't be alowed with USSD service platform |  | Pass
11 | Transfer to ATM | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Pass
|  | Enter the number entitled with "Transfer to ATM" and click "send" button | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
Negative scenario |  | Attempt to transfer exceeding Maximum limit (>8000) should not be applicable and throw error |  | Pass
|  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
14 | LMTS | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed |  | Not available
|  | Enter the number entitled with "LMTS" and click "send" button | select from account to debit TXN
|  | Enter NAME OF THE beneficiary | Enter father name
|  | Enter last name of the user | Enter phone number of the beneficiary
|  | Enter amount to be transferred and click on send button | Every entered detail will be displayed for confirmation
|  | Confirm with the entitled number and click on send button | Success for the transfer with TXN reference will be displayed and SMS will be delivered
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit
12 | Load to Telebirr | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Load to Telebirr" and click "send" button | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | The entered telebirr user should be verified and if it's not the system should throw an error accordingly |  | Not checked
|  | Attempt to transfer exceeding Maximum limit (>30,000) should not be applicable and throw error |  | Not checked
13 | Load To MPESA | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Not checked | Third party test unavailabile (to be tested on prod)
|  | Enter the number entitled with "Load to MPESA" and click "send" button | Enter phone number of MPESA wallet holder
|  | Wallet account verified and name of wallet holder will be displayed | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
Negative scenario |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | The entered M-PESA user should be verified and if it's not the system should throw an error accordingly |  | Not checked
|  | Attempt to transfer exceeding Maximum limit (>30,000) should not be applicable and throw error |  | Not checked
14 | Transfer to own account | Enter the number entitled with "Transfer to own account" and click "send" button | select from account to debit TXN | pass
|  | Enter the number entitled with prefered debit account and click "send" button | List of accounts other than the selected debit account will be displayed
|  | select preffered Credit account and click on "send" button | Enter amount to be transferred and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
Negative scenario |  | Even if the commulative is reached own account transfer should work with any amount |  | Pass
|  | If the account is inactive the process should throw an error and abort |  | Pass
15 | Transfer to other bank acc (Instant transfer) | Enter the number entitled with "Transfer to other bank" and click "send" button | select "Instant transfer" to transfer to other bank | Pass
|  | Select account holders bank name from listed banks | enter bank account number of the beneficiary
|  | account will be verified and displayed with name of the account holder | Enter amount to be transferred (</=50,000) and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
Negative scenarios |  | Comulative limit should not allow user to transfer more than the maximum USSD transfer limit |  | Pass
|  | Instant transfer to other banks aside from the cumulative limit should not allow the user to transfer more than 50k within a day |  | Pass
|  | Transfer TO USD accounts shouldn't be alowed with USSD service platform |  | Pass
16 | Transfer to other bank acc (Non- Instant transfer) | Enter the number entitled with "Transfer to other bank" and click "send" button | select "Non-instant transfer" to transfer to other bank | Pass
|  | Enter beneficiary name | select bank of the account holder among the provided list
|  | Enter beneficiaries account number | Enter amount to be transferred (</= 100,000 for one-time txn) and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
Negative scenarios |  | Comulative limit should not allow user to transfer more than the daily maximum USSD transfer limit |  | Pass
|  | Instant transfer to other banks aside from the cumulative limt should not allow user to transfer more than 50K for one time transfer |  | Pass
|  | Instant transfer to other banks aside from the cumulative limit should not allow the user to transfer more than 200k within a day |  | Pass
|  | Transfer TO USD accounts shouldn't be alowed with USSD service platform |  | Pass
17 | Ethiotel Airtime | Enter the number entitled with "Airtime" and click "send" button | select "Ethiotel Airtime" to Top up 09 network service numbers | Not checked | Third party test unavailabile (to be tested on prod)
|  | Select account to top up from | enter phone number and click "send" button
|  | Enter amount to Top-up | Detail to be confirmed will be displayed
|  | Confirm the detail with the entitled number | Success screen will be displayed with TXN reference
Negative scenario |  | Should not allow the user to top-up if daily commulative limit is reached |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | Phone number should start as 09 if not the process should throw error message to the user |  | Not checked
18 | Safaricom Airtime | Enter the number entitled with "Airtime" and click "send" button | select "Ethiotel Airtime" to Top up 09 network service numbers | Not checked | Third party test unavailabile (to be tested on prod)
|  | Select account to top up from | enter phone number and click "send" button
|  | Enter amount to Top-up | Detail to be confirmed will be displayed
|  | Confirm the detail with the entitled number | Success screen will be displayed with TXN reference
Negative scenario |  | Should not allow the user to top-up if daily commulative limit is reached |  | Not checked | Third party test unavailabile (to be tested on prod)
|  | Phone number should start as 07 if not the process should throw error message to the user |  | Not checked

## setting
Test # | Description of tasks | Steps To Execute | Expected Results | Status | Defect/Comments/Additions
MS001 | Exchange rate menu | Choose the Exchange rate option in the home page | List of currencies will be displayed | Pass
MS002 | De-subscribe service | Enter the number entitled with "My service' | Enter the entitled number with "De-subscribe" | Pass
|  | confirmation screen with Yes/No option will be displayed | Enter the entitled number with "Yes" and click on send button
|  | Enter pin to make sure the de-subscribing process | Success for the process will be displayed
M007 | My service | Enter the number entitled with "My service" and click "send" button | "Change Pin" and "De-subscribe" service will be displayed | Pass
Date | Functionalities | # of Functionalities | Pass | Fail | Not Executed
| Exchange rate | 3 | 3 | - | -

## CR (hidden)
*815# USSD test
S/N | Module | Excuted Features | Expected Results | Status | Remark
1 | Login | Click on "Login" button | Field to fill with credential will be displayed | Pass
|  | Enter your pin | Click on continue button and the page will get displayed with managing menus
2 | My Accounts | Enter the number entitled with "My accounts" and click "send" button | List of accounts associated with the user's customer ID will be displayed | Pass
|  | Select an account to check the transaction made within | Transaction of the given account will be displayed with date they were made
3 | Utilities | Enter the number entitled with "Utilities" and click "send" button | List of utility payment service menus will be displayed | pass
4 | Transfer | Enter the number entitled with "Transfer" and click "send" button | List of fund transfering options and money load wallets will be displayed | pass
5 | other bank Transfer | Enter the number entitled with "Transfer to other bank" and click "send" button | List of to other bank fund transfering options will be displayed | pass
6 | Airtime Topup | Enter the number entitled with "Airtime Topup" and click "send" button | List of Top up purchasing option service menus will be displayed | pass
7 | Exchange Rates | Enter the number entitled with "Exchange Rates" and click "send" button | List of exchange rate description will be displayed with next and previous option | pass
8 | My service | Enter the number entitled with "My service" and click "send" button | "Change Pin" and "De-subscribe" service will be displayed | pass
9 | Loan | Enter the number entitled with "Loan" and click "send" button | MESMER loan and an option to repay active loan "Repayment" will be displayed | pass
S/N | Service | Excuted Functionalities | Expected results | Status | Remark
1 | DERASH (Water Bill) | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Menu not found
|  | Enter the number entitled with "DERASH" and click "send" button | select city and enter client reference ID
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
2 | Awach | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "AWACH" and click "send" button | Enter account number of the beneficiary and account holder name will be displayed
|  | confirm account holder name by sending "1" | Amount entering screen will be displayed
|  | enter amount and click on "send" button | Remark entering screen will be displayed
|  | enter remark and click on the "Send" button | success for the payment with TXN reference will be displayed
3 | Canal Plus | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Lack of Test Data
|  | Enter the number entitled with "Canal Plus" and click "send" button | Enter client reference ID
|  | Package reference list will be displayed | select package preference (Existing, Desta, Feshta)
|  | Detail of the ID and selected package purchase amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
4 | Water | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Lack of Test Data
|  | Enter the number entitled with "Water" and click "send" button | select city and enter client reference ID
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
5 | Airlines | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Lack of Test Data
|  | Enter the number entitled with "Airlines" and click "send" button | Enter client order ID
|  | Detail along with payment amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | enter remark and click on the "Send" button | Success for the payment with TXN reference will be displayed
6 | DSTV | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Lack of Test Data
|  | Enter the number entitled with "DSTV" and click "send" button | Enter client Smart card number
|  | Package reference list will be displayed | select package preference (including an option for the Existing package)
|  | a list for subscription time interval (monthly, anually… etc) | select and confirm with "Send" button
|  | Detail of the ID and selected package purchase amount will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
7 | Websprix | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "Websprix" and click "send" button | Enter client ID/Websprix phone number
|  | Field to enter bill number will be displayed | enter bill number and click "Send" button
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
8 | Ethiotel bill | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "Ethiotelecom bill" and click "send" button | Enter bill phone number/Account key
|  | Field to enter bill number will be displayed | enter bill number and click "Send" button
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
9 | FHC (Federal Housing) | Enter the number entitled with "Utilities" and click "send" button | List of utility payment services will be displayed | Not checked | Lack of Test Data
|  | Enter the number entitled with "FHC" and click "send" button | Enter BILL reference
|  | A detail of Bill with amount to be paid will be displayed | Confirm the detail by entering "1" then remark field will be displayed
|  | Enter "Remark" and use the send button | Success for the payment with TXN reference will be displayed
10 | Transfer to other BOA acc | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "Transfer to other BOA acc" and click "send" button | Enter beneficiary account and verrify
|  | select from account to debit TXN | Enter amount to be transferred and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
11 | Transfer to ATM | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "Transfer to ATM" and click "send" button | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
14 | LMTS | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "LMTS" and click "send" button | select from account to debit TXN
|  | Enter NAME OF THE beneficiary | Enter father name
|  | Enter last name of the user | Enter phone number of the beneficiary
|  | Enter amount to be transferred and click on send button | Every entered detail will be displayed for confirmation
|  | Confirm with the entitled number and click on send button | Success for the transfer with TXN reference will be displayed and SMS will be delivered
12 | Load to Telebirr | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Failed | To be tested on prod
|  | Enter the number entitled with "Load to Telebirr" and click "send" button | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
13 | Load To MPESA | Enter the number entitled with "Transfers" and click "send" button | List of fund transfering options will be displayed | Failed | Enquiry has worked and Txn to be checked on Prod
|  | Enter the number entitled with "Load to MPESA" and click "send" button | Enter phone number of MPESA wallet holder
|  | Wallet account verified and name of wallet holder will be displayed | select from account to debit TXN
|  | Enter amount to be transferred and click on send button | Remark entering field will be displayed
|  | enter remark and continue | Success for the transfer with TXN reference will be displayed and SMS will be delivered
14 | Transfer to own account | Enter the number entitled with "Transfer to own account" and click "send" button | select from account to debit TXN | pass | To be tested on prod
|  | Enter the number entitled with prefered debit account and click "send" button | List of accounts other than the selected debit account will be displayed
|  | select preffered Credit account and click on "send" button | Enter amount to be transferred and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
15 | Transfer to other bank acc (Instant transfer) | Enter the number entitled with "Transfer to other bank" and click "send" button | select "Instant transfer" to transfer to other bank | Failed | Enquiry has worked and Txn to be checked on Prod
|  | Select account holders bank name from listed banks | enter bank account number of the beneficiary
|  | account will be verified and displayed with name of the account holder | Enter amount to be transferred (</= 25,000 for one-time txn) and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
16 | Transfer to other bank acc (Non- Instant transfer) | Enter the number entitled with "Transfer to other bank" and click "send" button | select "Non-instant transfer" to transfer to other bank | Failed | To be tested on prod
|  | Enter beneficiary name | select bank of the account holder among the provided list
|  | Enter beneficiaries account number | Enter amount to be transferred (</= 100,000 for one-time txn) and click on send button
|  | Remark entering field will be displayed | enter remark and continue
|  | Confirmation page with entered information will be displayed to be confirmed | Success for the transfer with TXN reference will be displayed
17 | Ethiotel Airtime | Enter the number entitled with "Airtime" and click "send" button | select "Ethiotel Airtime" to Top up 09 network service numbers | Failed | To be tested on prod
|  | Select account to top up from | enter phone number and click "send" button
|  | Enter amount to Top-up | Detail to be confirmed will be displayed
|  | Confirm the detail with the entitled number | Success screen will be displayed with TXN reference
18 | Safaricom Airtime | Enter the number entitled with "Airtime" and click "send" button | select "Ethiotel Airtime" to Top up 09 network service numbers | Failed | To be tested on prod
|  | Select account to top up from | enter phone number and click "send" button
|  | Enter amount to Top-up | Detail to be confirmed will be displayed
|  | Confirm the detail with the entitled number | Success screen will be displayed with TXN reference